## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed)
1 | Bhavya | 2025-11-10 | Number plate timestamps not displaying in results page due to incorrect DB column reference (plate_number KeyError). | Sprint 1 | Backend Team | Technical | Updated query to match vehicle_data.number_plate and corrected dictionary keys in app.py. | 2025-11-11 | Closed
2 | Backend Team | 2025-11-12 | ANPR model .pb file not loading due to incorrect relative model path. | Sprint 1 | Backend Team | Technical | Corrected absolute file path & added exception handling for missing model file. | 2025-11-12 | Closed
3 | Backend Team | 2025-11-14 | ATCC module was double-counting vehicles at frame intersections. | Sprint 2 | Backend Team | Functional | Added object tracking ID logic & frame-based filtering. | 2025-11-14 | Closed
4 | Frontend Team | 2025-11-16 | Upload button not calling Flask API due to incorrect JS fetch URL. | Sprint 3 | Frontend Team | User Interface | Corrected API endpoint URL & added CORS support. | 2025-11-16 | Closed
5 | Backend Team | 2025-11-17 | Flask server crashed when uploading large video files for ANPR/ATCC processing. | Sprint 4 | Backend Team | Performance | Increased request size limit, added streaming processing & improved memory handling. | 2025-11-17 | Closed
6 | Frontend Team | 2025-11-18 | Results (ANPR/ATCC output) not refreshing automatically on frontend dashboard. | Sprint 3 | Frontend Team | User Interface | Added JS auto-refresh logic & success callback for Flask response. | 2025-11-18 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others